## Sheet1
Project Schedule
Thema |  |  | : | Prevent Mixing at Taping Process with Marking Inspection
Prepared By |  |  | : | Zulhisham Tan
Date |  |  | : | 10th May 2011
No. | To Do | [6 empty] | May 2011
[8 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1. | Request Database from I.T. to retrieve mother | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 22; May 2011 28 to May 2011 29
Lot No. based on Taping Lot No. | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 22; May 2011 28 to May 2011 29
2. | Migrate Marking Database to Server | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 22; May 2011 28 to May 2011 29
3. | Software (PC) Construction | bar: May 2011 14 to May 2011 22; May 2011 28 to May 2011 29
4. | Wiring modification | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 23; May 2011 28 to May 2011 29
5. | Software Test & Debug | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 22; May 2011 28 to May 2011 29
6. | Test Run & Review | bar: May 2011 14 to May 2011 15; May 2011 21 to May 2011 22; May 2011 28 to May 2011 29
* Note |  | : | Task Completed
In Progress
Requirement
- | Special function for Lot inject
- | To be to detect Week Code Jumping
Taping with Marking Inspection System Integration
| Application Name |  |  |  |  | : | TapMarkInsp
| Outlook |  |  |  |  | : | - 80% Visibility. Optional Setting available.
- Located 30,30 pixels from Top-Left corner
the screen.
- Appear as Top-Most windows.
| Characteristic |  |  |  |  | : | A program which run as a background tasks
to monitor Keyboard and mouse event.
The program is created to capture the Lot
number and some others information which being entered into the system. It is an interface between the
Taping machine and the Vision Control system. The program responsible on signal interfacing between the
machine and the Vision control system. The responsibility were to select Inspection Scene, triggering the
Vision Control, Data Judgment as well as signalling the machine on 'GO'/'NoGO' pattern. A set of data is log
into the system database for future data tracking in order to address certain issue.
| Operation Format |  |  |  |  | : | - The 'Auto Run' operation of the machine will be interlocked whenever the application fail to capture Lot Data
which has being entered in to the system.
- The 'Auto Run' operation will also be interuppted if the marking data inspection judgment is fail.
- No any additonal operation were needed to handle the TapMarkInsp system. Everything is done automatically.
| Database |  |  |  |  | : | Marking data will be retrieved from the machine server located at I.T. room. The database is in Microsoft Access
format. Data were retrieve using SQL command.
| Deployment |  |  |  |  | : | The appilcation software is design to deploy via the network using IIS Server. Through the new deployment
concept, the verification of iM-Test Software control system is bypassed since the versioning of the software
is always varified through the server. Newer version of the application software will automatically updated
whenever a newer version of the application software is uploaded to the server.
The Modification Concept
| 1. | The 'TapMarkInsp' is development and setup into the Taping
machine's PC. The application is required Windows XP with
Service Pack 3 to run. It is complience to Windows 7 32bits as
well as 64 bits.
Please refer to 'Taping with Marking Inspection System
Integration' for its outlook and characteristic. No additional
operation were needed to operate the program.
| 2. | A USB Digital I/O card is attached to the PC. Listed below is the details of the USB-DIO card. The USB-DIO driver is installed to the PC of
the machine. It is being access by the 'TapMarkInsp'.
|  |  | Model |  |  | : | DIO-8/8B-UBC
|  |  | Maker |  |  | : | Y2 Coporation
|  |  | Qty |  |  | : | 1
|  |  | Reference |  |  | : | www.y2c.co.jp
| 3. | Eletrical wiring is being modify. As illustrated in the block disgram (1) below, wires that are connected from the PLC to the Vision
System (F-160) is being disconnected. It is attached to the new USB-DIO card as shown block diagram (2). The connection is refer
to the wiring diagram shown in Figure 1.
I/O bits between PC, PLC & camera unit
| 4. | As shown in the block diafram (2), the PC required 2 serial communication. The 1st comm. Port has been occupied by the original PC
program. As such, the 2nd comm. Port were needed to be added into the system. If the PC consists of 2 comm. Port then you may ignore
this step otherwise you may consider a USB-RS232 converter install to the system.
| 5. | At Laser Marking machine, the database were set to local drive as default. Hence, it is necessary to consider a commercial desktop PC
to act as server. Make a sharing folder to public, and then locate the Laser Marking database into the server. You need to change the
Laser Marking Barcode system setting to access to the database at the server.
Merits
| P | No software modification is needed to be to original PC Application.
| P | No additional operation were needed.
| P | Cycle time remain unchanged.
| P | Low modification cost.
| P | Able to complete within 3 to 4 days.
| P | PE/PM no longer needed to control IMI which would be database for the system to select scene file.
| P | Able to control week code jumping.
| P | Provide raw data for future reference.
| P | CPU resources were keep to minimum in order to give space to others application such as anti-virus program to effectively protect the
system.
System Integration
1. | Mr. Tee Tai Heng |  |  |  | - | Setting camera, Wiring Modification, Confirm system function.
2. | Zulhisham Tan |  |  |  | - | Development 'TapMarkInsp' application, Modified Laser Marking Database access.
1
2
19
20
Figure 1
PLC
F-160
PC
I/O
RS-232C
Block Diagram 1
PLC
F-160
PC
I/O
RS-232C
Block Diagram 2
Modify to
RS-232C
Port 7
Note on W15: 100% Completed
Note on AA17: I/O Check completed. Communication & Data Format has also confirm.

## Sheet2
Task :
R/P :
Duration :
Start :
End :
Delay :
Rmk :
Task : Migrate LM Database To Server
R/P : Zulhisham Tan
Duration : 0.1
Start :
End :
Delay :
Rmk : Database
Task : Capture Keyboard Event Software
R/P : Zulhisham Tan
Duration : 3
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : Electrical Wiring Modification
R/P : Tee Tai Heng
Duration : 0.2
Start :
End :
Delay :
Rmk :
Task : Camera Setting
R/P : Tee Tai Heng
Duration : 0.4
Start :
End :
Delay :
Rmk :
Task : M/C Performance & Stability
R/P : Elham
Duration : 2
Start :
End :
Delay :
Rmk :
Task : Establish Vision Communication
R/P : Zulhisham & Tee Tai Heng
Duration : 0.5
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : I/O Confirmation
R/P : Zulhisham & Tee Tai Heng
Duration : 0.1
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : Total System Eveluation
R/P : Z_Tan, Tee Tai Heng & Elham
Duration : 1
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : Design System User Interface
R/P : Zulhisham Tan
Duration : 2
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : Install Software Components
R/P : Zulhisham
Duration : 0.2
Start :
End :
Delay :
Rmk : Soft. Dev.
Task : Trial Run
R/P : Z_Tan, Tee Tai Heng & Elham
Duration : 0.5
Start :
End :
Delay :
Rmk : Soft. Dev.